| Period | PWG Reliability Plan Action | PWG Enhanced Access Plan Action | OSC Activities |
| --- | --- | --- | --- |
| Sept05 - Nov05 | Recommend assumptions and criteria for the combined Duke/Progress reliability plan and submit to OSC for approval prior to 11/2 OSC meeting |  | 11/2: OSC meeting to discuss compare/contrast document submitted by PWG for reliability and enhancement plans |
| Dec05 - Jan06 | Build & finalize models w/ new VSTE | Discuss assumptions and criteria for the combined Duke/Progress enhanced access plan and submit a compare/contrast document to OSC for approval prior to 12/9 OSC meeting | 12/9: OSC meeting to approve reliability assumptions and criteria; OSC continues discussion of enhancement assumptions and criteria 1/5: OSC meeting to approve enhancement assumptions and criteria 1/15: Lists of requested enhancement studies due from Participants and TAG (Carney & Locke to compile for 1/30) 1/30: OSC meeting to discuss enhancement study requests and draft preliminary study list |
| Feb06 – Mar06 | Perform screens for the reliability plan Report results to OSC prior to 3/30 | PWG receives preliminary list of enhanced access study requests on 2/28 Develop estimated costs and schedules for preliminary enhanced study requests and provide to OSC prior to 3/30 | 2/28: OSC meeting to approve list of enhanced access projects/alternatives for preliminary study; OSC submits list to PWG to estimate study costs and schedules 3/30: OSC meeting to review cost/schedule of preliminary enhancement studies submitted by PWG |
| Apr06-May06 | Determine alternatives, estimated costs and schedule, and select preferred alternatives for reliability plan Report results to OSC prior to 5/1 & obtain OSC approval for preferred alternatives | PWG receives approved list on 5/1 of enhancement requests to be studied in detail | 5/1: OSC meeting to select enhancement requests and alternatives to be studied in detail and submitted to PWG; OSC begins discussions of 2006/2007 budget for the Process and Gestalt 5/2: OSC informs TAG of study status |
| Jun06 | Final reliability plan & report to OSC Prior to 6/30 | VSTE models available on 6/15 PWG provides potential alternatives to achieve desired levels of transfer capability and update OSC on 6/30 PWG begins enhanced access studies (VSTE model version TBD, based on nature of studies to be solved) | 6/30: OSC approves 2006/2007 NCTPC budget; PWG updates OSC on potential alternatives to achieve desired levels of transfer capability |
| Jul06-Aug06 |  | Provide OSC with planning-level estimates of construction costs and schedules for enhancement projects prior to 7/30 | 7/30: OSC discusses potential enhancement projects 8/31: OSC selects enhancement projects and provides to PWG for refinement; OSC starts project cost allocation discussion |
| Sept06-Nov06 | Refine costs and schedules of reliability plan and report results to OSC prior to 10/20 Integrate/iterate reliability plan with enhancement plan and report results to OSC prior to 11/20 | PWG receives selected enhancement projects on 8/31 Refine costs and schedules of enhanced access project plan and report results to OSC prior to 10/20 Integrate/iterate enhancement plan with reliability plan and report results to OSC prior to 11/20 | 10/20: OSC reviews any refinements of enhancement and reliability projects; OSC approves enhancement projects/plan and submits to PWG for integration with reliability plan 11/20: OSC approves final reliability and enhancement projects and combined reliability/enhancement plan 11/21: OSC informs TAG of final collaborative plan |
| Dec06 |  |  | 12/15: OSC completes cost allocation and budget discussions for combined reliability and enhancement plans |